## Slide 1
Unit 2
Planning the fieldwork
Notes: Welcome to Unit 2 of Module 6.

## Slide 2
By the end of this unit, you will be able to:
describe the different activities to plan ahead of data collection
list all the materials and tools necessary for data collection
Notes: By the end of this unit, you will be able to:
describe the different activities to plan ahead of data collection;
list all the materials and tools necessary for data collection.

## Slide 3
Contact authorities in advance
national survey manager
managing authority
There should be advance contact with authorities
notify appropriate authorities of the nature and purpose of the health facility assessment
send an official letter to the regional or district offices for that organization
Notes: Ahead of any fieldwork planning, there should have been advance contact with authorities:
​
the national survey manager will have notified appropriate authorities of the nature and purpose of the health facility assessment in advance of the fieldwork; ​
the managing authority for the facilities being surveyed should have sent an official letter to the regional or district offices for that organization.

## Slide 4
team leader
Planning fieldwork
area supervisor
Notes: Fieldwork planning involves the data collection team leader and the area supervisor.
Let’s look at the activities involved.

## Slide 5
Planning fieldwork​
provider adherence to standards
1
Prepare materials and tools
2
Plan data collection visits
3
Arrange for transport
4
Confirm appointments
5
Assign questionnaire sections
Notes: Prepare materials and tools​;
Plan data collection visits​;
Arrange for transport​;
Confirm appointments​;
Assign questionnaire sections​.
​
We’ll now look at each activity in more detail.​
​

## Slide 6
Prepare materials and tools for data collectors
provider adherence to standards
contact details of area supervisor
official identification document
electronic data collection device
back-up devices
mobile phones, internet access and airtime
electronic copy of questionnaire
list of facilities to be visited
blank consent forms
notebook and pen
details of facility in-charge
Notes: Preparing materials and tools for data collectors involves providing:
the contact details of the area supervisor;
the official identification document with a photograph;
the electronic data collection device with the finalized CSPro tool;
a back-up device for each team;
mobile phones, internet access and airtime for each team;
an electronic copy of the final paper questionnaire for reference;
a list of facilities to be visited, with facility opening hours and a map showing the facility location;
the name and contact details of the person in charge at each facility;
blank consent forms for each team; and
a notebook and pen to record any significant events, findings, or challenges.

## Slide 7
Area supervisor
Plan data collection visits
establishes appointment date
prepares a written schedule of facility visits
Team leader
prepares a list of the sampled health facilities
Notes: To plan data collection visits:
the area supervisor prepares a list of the sampled health facilities in each geographic area, including the location of each health facility, and the name and contact details of the person in charge;
the team leader contacts the person in charge at each facility in advance to establish an appointment date and time for the data collection visit.
Before data collection starts, the team leader prepares a written schedule of facility visits for their data collection team and shares this with their team members and area supervisor.

## Slide 8
Area supervisor
Arrange for transport
arranges for transport and regular communication
the facilities to be visited
the number of teams involved
the number of people per team
Data collectors may also be provided with an allowance to organize their own transport.
Notes: After receiving the schedule of visits from the team leaders, the area supervisor arranges transport and regular communications according to:
the facilities to be visited;
the number of teams involved; and
the number of people per team.
Or, data collectors may also be provided with an allowance to organize their own transport.

## Slide 9
Confirm appointments
confirms appointments with health facilities
Team leader
Notes: The team leader contacts each health facility the day before the scheduled data collection visit to confirm the appointment.

## Slide 10
Assign questionnaire sections
assigns questionnaire sections to data collectors
Team leader
Data collector
Notes: Before visiting the facility, the team leader assigns the required sections of the questionnaire for that facility to the data collectors, ensuring that the sections are appropriately distributed among the data collectors.

## Slide 11
You have now completed Unit 2.
In the next unit, we will look at data collection procedures in the field.
First, try the practice exercise.
Notes: You have now completed Unit 2.
In the next unit, we will look at data collection procedures in the field.
First, try the practice exercise.