Module 6. Practice (with right answers ticked in blue):

Sort chronologically the planning activities for the field work:

* Assign questionnaire sections to data collectors **(6)**
* Arrange for transport and regular communication **(4)**
* Prepare materials and tools for data collectors **(2)**
* Plan data collection visits **(3)**
* Advance contact with local authorities **(1)**
* Confirm appointment with health facilities **(5)**